## Dashboard
BlackStage OS Development Tracker
Updated 2026-05-14. Repo-backed tracker now includes cinematic render-system study, StageSceneManifest contract, Browser-first visual QA, and live-harness evidence.
Metric | Value | Notes | Source | Backlog Status | Count
Backlog Tasks | 20 | Total initial tasks | Backlog | Done | 16
Done Tasks | 16 | Completed items | Backlog | In Progress | 3
In Progress Tasks | 4 | Active work | Backlog | Blocked | 4
P0 Tasks | 14 | Critical path | Backlog | Not Started | 0
Open Risks | 6 | Risks not closed | Risk Register | Deferred | 0
Planned Experiments | 5 | Research experiments awaiting run | Experiments
Open Checklist Items | 1 | Checklist items not done | Checklists
Next Action | Owner | Status
Build StageSceneField vector layer and live voice debug overlay | Codex | In Progress
Run human live microphone session | Cheick | Open
Promote one-command live voice runner | Codex | Open
Taste-review active render field after voice pass | Cheick | Open
Use Browser plugin for manual visual QA | Codex | Done
Keep approval-gated local harness hardening | Codex | In Progress

## Roadmap
Phase | Target | Objective | Key Deliverables | Exit Criteria | Status | Owner | Research Questions | Notes
0 Foundation | Week 0-1 | Create repo, docs, operating model, tracker, and first design direction. | Repo initialized; AGENTS.md; docs; package structure; research templates. | Codex can understand mission and run basic commands. | Done | Cheick + GPT-5.5 Pro + Codex | Which docs most improve Codex output? | Repo bootstrapped; docs, commands, tracker, and research loop live.
1 Stage Shell v0 | Week 1-3 | Prove the living render field. | Black stage; center presence; intent threads; simulated agent feed; approvals; artifacts; fixtures. | Viewer says this is not a chatbot and wants to try it. | In Progress | Codex | Does visible agent labor increase trust? | Stage Shell v0 works locally; active render field and live voice polish continue.
2 Real Conversation + Artifact Engine | Week 3-6 | Move from simulation to model-backed conversation and artifact creation. | Realtime conversation; structured render manifest; artifact generation; export. | System creates useful artifacts from real user intent. | In Progress | Codex | When does render beat chat? | Realtime broker/tool contracts, local voice paths, and artifact workbench exist; human mic pass open.
3 Agent Runtime + Approval System | Month 2 | Introduce real delegated work under strict human control. | Task model; tool adapter; approval policy; audit log; cancellation; evidence. | Agents perform bounded useful tasks safely. | In Progress | Codex | What approval rituals reduce fear without friction? | Local harness contracts, approvals, action packets, and proof packets exist; live external work gated.
4 Knowledge Work Operating Layer | Month 3-4 | Connect to real knowledge workflows. | File/browser/research portals; workspace search; project memory; artifact library. | Founder can use Blackstage for daily knowledge work. | Planned | Team | Do intent threads beat folders/chat history?
5 Multi-Agent Command Center | Month 4-6 | Coordinate multiple agents across complex workflows. | Roles; subagents; summaries; conflict resolution; performance metrics. | Multiple agents work without chaos. | Planned | Team | What subagent workflows improve quality?
6 Personal Cognitive OS | 6-12 months | Make Blackstage the user's primary interface for thinking and execution. | Memory vault; cross-device continuity; proactive suggestions; deep artifact management. | Users start in Blackstage before opening apps. | Future | Team | What is a safe personal AI memory model?
7 Ambient Reality Interface | 12+ months | Extend from computer interface to reality interface. | Multimodal context; wearables; devices/robotics; real-world approvals. | Blackstage mediates digital and physical environments. | Future | Team | How do approval rituals scale to the physical world?

## Backlog
ID | Workstream | Phase | Task | Status | Priority | Owner | Acceptance Criteria | Verification | Research Log Required | Dependencies | PR Link | Due Date | Notes
BS-001 | Foundation | 0 Foundation | Initialize monorepo and workspace commands | Done | P0 | Codex | Repo has apps/packages structure and install/dev/build/typecheck commands. | Workspace commands exist; repo builds/typechecks. | Yes
BS-002 | Foundation | 0 Foundation | Install AGENTS.md and docs into repo root | Done | P0 | Cheick + Codex | Codex can summarize project mission and active instructions. | AGENTS.md and operating docs are installed. | Yes | BS-001
BS-003 | Core State | 1 Stage Shell v0 | Define IntentThread, StageObject, AgentEvent, ApprovalRequest, Artifact, ResearchEvent types | Done | P0 | Codex | Types exported from stage-core and used by app. | stage-core types drive the app/runtime tests. | Yes | BS-001
BS-004 | Stage Frontend | 1 Stage Shell v0 | Build full-screen black StageRoot and PresenceCore | Done | P0 | Codex | Idle stage looks cinematic and not like chatbot. | Orb-first cinematic idle field is e2e covered. | Yes | BS-001
BS-005 | Stage Frontend | 1 Stage Shell v0 | Add text intent submission and transcript display | Done | P0 | Codex | User submits intent and sees it captured as first-class object. | Text intent creates first-class stage objects. | Yes | BS-003, BS-004
BS-006 | Core State | 1 Stage Shell v0 | Create intent thread reducer and local persistence | Done | P0 | Codex | Threads persist across reload and can be resumed. | Serializable thread persistence/replay exists. | Yes | BS-003
BS-007 | Agent Runtime | 1 Stage Shell v0 | Implement simulated agent event stream | Done | P0 | Codex | Activity feed streams planned/started/progress/completed/approval_needed events. | Simulated and local harness labor streams are visible. | Yes | BS-003
BS-008 | Stage UI | 1 Stage Shell v0 | Build IntentCard, PlanCard, AgentActivityFeed | Done | P0 | Codex | Cards render from typed StageObjects and preserve visual thesis. | Core cards render; Render Field Layout v1 is underway. | Yes | BS-004, BS-007
BS-009 | Trust | 1 Stage Shell v0 | Build ApprovalCard and approval history | Done | P0 | Codex | Approval card shows action, scope, risk, consequence, undo path. | Approval cards/history gate high-impact actions. | Yes | BS-003, BS-007
BS-010 | Artifacts | 1 Stage Shell v0 | Build ArtifactCard and CodexTaskCard | Done | P0 | Codex | Approving creates artifact/Codex task cards. | Approval creates editable/exportable artifacts. | Yes | BS-009
BS-011 | Research | 1 Stage Shell v0 | Implement local research event logger | Done | P0 | Codex | Key product events logged with session ids and timestamps. | Research/stage events export locally. | Yes | BS-003
BS-012 | Research | 1 Stage Shell v0 | Add session event export and research note generator | Done | P1 | Codex | User can export JSON and create markdown note draft. | JSON trace export and markdown research logs exist. | Yes | BS-011
BS-013 | Stage UX | 1 Stage Shell v0 | Add demo fixtures: Build Blackstage, Acquisition Analysis, Research Synthesis | Done | P0 | Codex | Fixture selector runs each demo without private data. | Fixture demos are hidden from startup; tests cover idle. | Yes | BS-007, BS-008
BS-014 | Voice | 2 Conversation | Add voice input experiment | In Progress | P1 | Codex | User can submit spoken intent or use fallback text. | Browser speech works; human Realtime mic pass remains. | Yes | BS-005
BS-015 | Artifacts | 2 Conversation | Implement markdown artifact export | Done | P1 | Codex | Artifacts export as markdown with provenance. | Markdown export covered by e2e download flow. | Yes | BS-010
BS-016 | Trust | 3 Agent Runtime | Implement approval policy engine | In Progress | P0 | Codex | External/financial/credential/destructive actions always require approval. | Approval policy exists; live external execution remains gated. | Yes | BS-009
BS-017 | AI Building | 3 Agent Runtime | Add Codex task export artifact | Done | P1 | Codex | Stage can generate Codex-ready task briefs from an intent thread. | Codex task briefs/action packets are artifacts. | Yes | BS-010, BS-012
BS-018 | Quality | 1 Stage Shell v0 | Create visual QA screenshots for demo states | In Progress | P1 | Codex | Screenshots show idle, working, approval, artifact states. | Render organization intelligence v1 added; Browser-plugin visual QA still needs Cheick taste review. | Yes | BS-004, BS-008, BS-009
BS-019 | Stage Rendering | 1 Stage Shell v0 | Create cinematic scene manifest and fluid vector renderer | In Progress | P0 | Codex | IntentThread compiles to scene manifest; UI renders semantic roles, edges, and liquid field without dashboard feel. | stage-core/stage-web typecheck; Browser-plugin screenshot; e2e visual assertions. | Yes | BS-003, BS-008, BS-018 |  |  | Manifest contract started from video/json-render study; Phase 1 vector field next.
BS-020 | Stage Frontend | 1 Stage Shell v0 | Browser compact render QA and orb voice entry | Done | P0 | Codex | Browser in-app compact viewport keeps active stage regions separated and live voice/debug controls reachable. | Browser plugin geometry check reports zero overlaps and visible Speak/Export controls. | Yes | BS-018, BS-019 |  |  | Logged in 2026-05-15 browser compact render slice.
BS-021 | Stage Rendering | 1 Stage Shell v0 | Make render field the goal center: semantic stage coordinates and focal floor | Done | P0 | Codex | Active field uses scene coordinates, a focal floor/horizon, hidden QA deep links, and Browser evidence without visible demo buttons. | Browser desktop/mobile visual QA; typecheck/lint/build/test | Yes | BS-019, BS-020 |  | 2026-05-15 | Next: central approval ritual and geometric agent labor.
BS-022 | Stage Rendering | 1 Stage Shell v0 | Turn approval and agent labor into central cinematic scene objects | Planned | P0 | Codex | Pending approvals dim the field and become central ritual objects; agent labor can expand from geometry into audit feed. | Browser visual QA plus e2e scene-manifest assertions | Yes | BS-021 |  |  | Reference video frames show approval/action and labor geometry as the next gap.

## Experiments
ID | Track | Question | Hypothesis | Method | Primary Metric | Status | Owner | Start Date | End Date | Result | Evidence Link | Notes
EXP-001 | Product/HCI | Does a living render field feel meaningfully different from chat? | Users will rate Blackstage higher on wow/control than chat-only. | Compare same task in chat-only vs Stage Shell. | Wow score; perceived control | Active | Cheick
EXP-002 | Product/HCI | Does visible agent labor increase trust? | Activity feed improves trust and reduces anxiety. | A/B demo with feed hidden vs visible. | Trust score; intervention count | Active | Cheick
EXP-003 | Product/HCI | Are approval rituals clear without feeling bureaucratic? | Structured approval cards improve safety perception. | User demo and interview. | Approval clarity score | Active | Cheick
EXP-004 | AI Build | Do detailed docs improve Codex first-pass success? | Tasks with docs referenced will need fewer correction turns. | Compare tasks with/without doc references. | First-pass success; correction count | Active | GPT-5.5 Pro
EXP-005 | AI Build | Do subagents improve review quality? | Specialized reviewers catch more severe issues. | Single review vs multi-subagent review. | Severity-weighted findings | Planned | Codex

## Research Logs
Log ID | Date | Type | Related Task/Experiment | Prompt/Scenario | What Worked | What Failed | Human Interventions | Product Insight | AI-Building Insight | Evidence Link | Next Action
LOG-001 | 2026-05-10 | Build | BS-001 | Bootstrap repo
LOG-002 | 2026-05-14 | UX/Build | BS-018 | Render Field Layout v1 | Spatial object constellation, typed light accents, mobile/tablet resets. | Needs Cheick taste review after live voice session. | None | Active workspace must feel summoned, not opened as panels. | E2E now checks visual structure, not only DOM presence.
LOG-003 | 2026-05-14 | Ops/Research | Tracker | Refresh stale Excel tracker from repo evidence | Backlog, roadmap, risks, checklists, and next actions now reflect current repo state. | Artifact-tool runtime was unavailable, so the workbook was updated in place via direct OOXML. | None | The tracker must be an operational source of truth, not a bootstrap artifact. | Durable project state prevents goal loops from losing the current frontier.
LOG-004 | 2026-05-14 | UX/Build | BS-018 | Render organization intelligence pass | Primary plan display, topology strip, cleaner command rail, and short-viewport collision handling. | First Browser screenshot exposed crowding; second pass hid secondary chrome in shallow viewport. | Cheick flagged lack of organization intelligence and display quality. | Hierarchy has to be legible before live tool use feels magical. | Browser-plugin validation catches compact-surface overlap missed by large screenshots.
LOG-005 | 2026-05-14 | UX/Research | BS-019 | Study cinematic demo video and json-render prior art | Extracted video frames, inspected json-render, and added StageSceneManifest contract. | No live aesthetic validation yet; next slice must prove the vector field visually. | Cheick supplied target video and called current display not good enough. | The target is a cognitive scene system, not prettier cards. | Borrow guarded specs and patch streams from json-render, but render scene semantics. | docs/research/runs/2026-05-14-cinematic-render-system-study.md | Build StageSceneField vector layer and Browser screenshot gate.
LOG-006 | 2026-05-15 | UX/Validation | BS-020 | Browser compact render and orb entry QA | Idle orb is demo-free; compact active field keeps intent, plan, evidence, labor, approval, artifact, command, and research zones separated. | Initial compact pass hid command/debug; focused dock then overlapped the document object before the one-row compact fix. | Cheick explicitly corrected tool choice to Browser plugin. | Quiet chrome must stay reachable; hidden controls cannot block live testing. | Browser plugin catches real in-app viewport issues that headless gates can miss. | docs/research/runs/2026-05-15-browser-compact-render-and-orb-entry-slice.md | Continue StageSceneField vector layer and live voice debug QA.
LOG-007 | 2026-05-15 | UX/Research | BS-021 | Frame-by-frame render field reference analysis | Extracted all 192 frames and translated the video into stage, focal, approval, and labor requirements. | Confirmed prior UI still leaned too much toward cards/dashboard composition. | Cheick supplied a second cinematic reference and redirected the goal toward rendering field animation. | One focal object plus orbiting support reads smarter than many equal panels. | Frame sampling turned taste feedback into concrete renderer requirements. | docs/research/runs/2026-05-15-render-field-reference-analysis.md | Build central approval ritual and geometric labor field.
LOG-008 | 2026-05-15 | UX/Build | BS-021 | Semantic stage-coordinate render pass | StageSceneManifest now drives x/y/depth/scale; StageSceneField draws focal floor and horizon; Browser QA shows no active-field overlaps. | Browser input path exposed clipboard limitations, so hidden scenario/instant QA links were added. | None beyond Cheick's rendering-first correction. | The field must own organization; CSS grid placement is not enough. | Browser visual checks need deterministic deep links that do not pollute startup UX. | docs/research/runs/2026-05-15-stage-scene-field-vector-slice.md | Make approval and labor materialize as central scene states.

## Decision Log
Decision ID | Date | Area | Decision | Status | Owner | Rationale | Options Considered | Evidence Link | Review Date | Notes
DEC-001 | 2026-05-10 | Product | Start with Stage Shell v0 before full OS replacement. | Accepted | Cheick | Prove the living render field before broad integrations. | Full OS; browser prototype; design-only mock | docs/06_mvp_stage_shell_spec.md
DEC-002 | 2026-05-10 | Research | Instrument product and build process from day one. | Accepted | Cheick + GPT-5.5 Pro | Research output is part of the mission. | Add later; manual notes; instrument now | docs/14_research_protocol.md
DEC-003 | 2026-05-14 | Product | Startup stays orb-first; fixture demos remain hidden from the first screen. | Accepted | Cheick + Codex | The user should click the orb and speak, not choose a demo. | Visible demo buttons; blank chat; orb-first field | apps/stage-web/tests/stage-shell.spec.ts | 2026-05-21
DEC-004 | 2026-05-14 | Rendering | Active work should render as a spatial field of cognitive objects, not a dashboard grid. | Accepted | Cheick + Codex | The category thesis depends on a calm living render field around intent. | Two-column cards; spatial constellation; full 3D scene | docs/research/runs/2026-05-14-render-field-layout-v1-slice.md | 2026-05-21
DEC-005 | 2026-05-14 | Validation | Manual rendered QA should use the Browser plugin before standalone Playwright fallback. | Accepted | Cheick + Codex | Cheick explicitly requested Browser for testing rendered local UI. | Standalone Playwright only; Browser-first visual QA | docs/research/runs/2026-05-14-render-organization-intelligence-slice.md | 2026-05-21
DEC-006 | 2026-05-14 | Rendering | Blackstage render system will use a guarded scene manifest and patch stream, not arbitrary generated UI or static cards. | Accepted | Cheick + Codex | The video target requires cinematic scene semantics while preserving replayability and approval safety. | Static CSS cards; arbitrary agent DOM; json-render component tree; Blackstage scene graph. | docs/28_cinematic_rendering_system.md | 2026-05-21 | Inspired by json-render contracts, adapted for camera, substrate, material, motion, clusters, and edges.
DEC-007 | 2026-05-15 | Rendering | Compact active sessions must keep voice and debug entrypoints reachable instead of hiding them completely. | Accepted | Cheick + Codex | Live testing depends on visible Speak and debug export controls even when the field is intentionally quiet. | Hide all chrome; always show full panels; compact one-row command and trace controls | docs/research/runs/2026-05-15-browser-compact-render-and-orb-entry-slice.md | 2026-05-22 | Browser plugin geometry check is the acceptance gate for compact active sessions.
DEC-008 | 2026-05-15 | Rendering | The active goal is rendering-first until the field itself feels like organized intelligence. | Accepted | Cheick + Codex | The project thesis fails if runtime features work but the surface still reads like a dark dashboard. | Continue backend/runtime first; polish cards; render-field-first goal amendment. | codex/goals/first_long_run_stage_shell_v0_after_prompt1.md | 2026-05-22 | Reference video 2 is now a north-star artifact for stage composition and motion.
DEC-009 | 2026-05-15 | Validation | Use hidden deep-link QA parameters for visual scenarios instead of visible demo buttons. | Accepted | Codex | The startup UX must remain one orb and one instruction while Browser QA still needs deterministic active states. | Visible demo buttons; manual typing only; hidden query controls. | docs/28_cinematic_rendering_system.md | 2026-05-22 | Supported query controls: stageScenario, stageIntent, stageInstant, stageDelayMultiplier.

## Risk Register
Risk ID | Area | Risk | Severity | Probability | Impact | Mitigation | Owner | Status | Trigger | Notes
R1 | Product | Blackstage feels like a chatbot with a black background. | Critical | Medium | Kills category thesis. | Orb-first idle, scene manifest contract, and spatial render field; continue vector-field and taste QA after live sessions. | Cheick | In Progress | UI dominated by chat bubbles.
R2 | Product | Interface feels too abstract or intimidating. | High | Medium | Users don't understand how to use it. | Use orb-first startup, progressive reveal, and live debug/taste sessions. | Cheick | Open | Users ask 'what do I do?'
R3 | Trust | Users don't trust agent actions. | Critical | Medium | Delegation fails. | Visible labor, approvals, evidence, and audit logs exist; real live trust still needs testing. | Team | In Progress | Users hesitate to approve.
R4 | Technical | Overbuilding architecture too early. | High | High | Slows demo progress. | Continue vertical slices with validation and incremental commits. | Codex | Mitigated | Too many packages before working demo.
R5 | Research | Research logs leak private information. | High | Low | Privacy breach. | Keep redaction and no-secret gates; local env files remain ignored. | Team | Open | Logs contain private transcripts.
R6 | AI Build | Codex implements generic UI and loses taste. | High | High | Product becomes undifferentiated. | StageSceneManifest moves taste-critical organization into code; Browser-plugin visual QA remains the gate. | GPT-5.5 Pro | In Progress | Looks like SaaS dashboard.

## Checklists
Area | Item | Status | Owner | Due Date | Evidence/Notes
Codex Task | Task has clear objective | Done | Cheick |  | Goal run objective is explicit in AGENTS.md and audit docs.
Codex Task | Relevant docs named | Done | Cheick |  | Relevant docs and runbooks are committed.
Codex Task | Acceptance criteria explicit | Done | Cheick |  | Acceptance criteria are carried in specs/tests.
Codex Task | Verification commands listed | Done | Cheick |  | Validation commands are listed in tracker/docs.
PR | Build passes | Done | Codex |  | Full build gate is part of this checkpoint.
PR | Typecheck passes | Done | Codex |  | Stage Web typecheck passed for this slice.
PR | UI still feels like Blackstage | In Progress | Cheick |  | Render organization intelligence v1 added; Cheick taste review remains open.
Stage Shell v0 | Full-screen black stage | Done | Codex |  | Orb-first black living field e2e covered.
Stage Shell v0 | Intent thread creation | Done | Codex |  | Intent thread creation e2e covered.
Stage Shell v0 | Simulated agent event stream | Done | Codex |  | Visible simulated/local harness labor exists.
Stage Shell v0 | Approval card | Done | Codex |  | Approval cards cover action/scope/consequence/status.
Stage Shell v0 | Artifact card | Done | Codex |  | Artifacts can be edited, approved, and exported.
Research | Session logs created | Done | Team |  | Research logs exist under docs/research/runs.
Security | No secrets in code | Done | Team |  | scan:secrets is maintained as a gate.
Security | No external side effects without approval | Done | Team |  | External side effects remain approval-gated/local-only.

## Source Notes
Source | URL | How it informed this tracker
OpenAI Codex introduction | https://openai.com/index/introducing-codex/ | Codex can work on coding tasks, answer codebase questions, fix bugs, and propose PRs in isolated environments.
Codex best practices | https://developers.openai.com/codex/learn/best-practices | AGENTS.md should include repo layout, commands, conventions, constraints, and definition of done.
Codex AGENTS.md guide | https://developers.openai.com/codex/guides/agents-md | Repo-level and directory-level instructions guide agent behavior.
Codex approvals and security | https://developers.openai.com/codex/agent-approvals-security | Sandboxing and approval policies should govern risky work.
Codex sandboxing | https://developers.openai.com/codex/concepts/sandboxing | Sandbox defines technical boundaries; approval policy controls when Codex stops to ask.
Codex subagents | https://developers.openai.com/codex/subagents | Subagents can be used for specialized review and parallel analysis when explicitly requested.
Codex GitHub reviews | https://developers.openai.com/codex/integrations/github | AGENTS.md review guidelines can influence PR review behavior.
Codex models | https://developers.openai.com/codex/models | Use strongest available model for complex coding/research, smaller models for lighter tasks/subagents.